## 🏠 Start Here
NESTS · Material Cost Estimator 2026
Zimbabwe Market Focus ¦ Budget your residential build with confidence
📋 WHAT IS THIS TOOL?
This Excel tool mirrors the NESTS online platform experience. It helps you estimate building material and labour costs before you post a project — so you arrive informed when vendors submit their bids.
When you post a project on NESTS, vendors complete the same phases and milestones you see in this workbook. When a vendor wins, the NESTS system generates a downloadable bid document — this spreadsheet previews that format.
Spot Checker gates (Stage 1–7) are NESTS independent inspections that unlock payment at key milestones. Fees are shown for transparency but are separate from your build budget.
📑 WORKBOOK TABS — WHAT EACH SHEET DOES
🏠 Start Here | This page — overview and instructions
📐 Project Setup | Enter your project details, location, and house size
🧱 Materials Estimator | Price out all major building materials by phase
👷 Labour Rates | Reference NEC wage rates; estimate your labour budget
🚀 HOW TO USE — 5 STEPS
Step 1 | Go to 📐 Project Setup — fill in your name, location, house type, and total budget.
Step 2 | Open 🧱 Materials Estimator — adjust quantities for each phase. Unit prices auto-populate from the 2026 reference rates. Edit any price in blue.
Step 3 | Check 👷 Labour Rates — see NEC-graded rates for Zimbabwe. Enter estimated labour days per phase to get a labour subtotal.
Step 4 | Review 📊 Bid Summary — see your full budget across materials + labour, with Spot Checker fees shown separately.
⚠ DISCLAIMER
All prices are indicative estimates based on ZimStat BMPI Q1 2026, CAHF Africa Housing Finance Yearbook 2024, AECOM Africa Cost Guide 2024/25, and market sources.
Prices vary by location, supplier, season, and project scale. Urban Harare prices are used as base. Bulawayo and secondary cities may be 5–15% lower.
Labour rates reflect NEC-CI minimum wages (Circular 02/2024). Actual market rates may differ. This tool is for budgeting guidance only — not a contract or quote.
NESTS Spot Checker fees and council inspection fees shown for transparency. These are separate from your construction budget and payable to NESTS / Harare City Council.
© 2026 NESTS. All rights reserved. For informational purposes only. Not financial or legal advice. Always consult a qualified quantity surveyor for formal estimates.
NESTS · nests.africa · Building Intelligence Across Africa · 2026

## 📐 Project Setup
📐 PROJECT SETUP
Fill in the yellow cells below. These values feed into your Materials Estimator and Bid Summary.
👤 CLIENT & PROJECT DETAILS (blue cells = you edit these)
Your Name / Organisation | Sarah M. | ℹ Who is the project owner?
Project Name | Harare Residential Build — 4-Bedroom | ℹ Give your project a clear title
Site Location | Borrowdale, Harare | ℹ City/suburb — affects price baseline
Province / Region | Harare Metropolitan
Proposed Start Date | 20 Jun 2026 | ℹ When do you plan to begin construction?
Target Completion | 31 Dec 2026 | ℹ Realistic timeline for full project
🏗️ HOUSE SPECIFICATIONS
House Type | 4-Bedroom Executive | ℹ e.g. 3-Bed Standard, 4-Bed Executive, 5-Bed Luxury
Total Floor Area (m²) | 180 | ℹ Your gross floor area — drives material quantities
Number of Bedrooms | 4
Number of Bathrooms | 3
Storeys | Single Storey | ℹ Single Storey or Double Storey
Finish Level | Executive / High Quality | ℹ Basic ¦ Standard ¦ Executive ¦ Luxury
Wall Type | Face Brick External / Common Internal
Roofing Type | Chromadek IBR Sheets on Timber Trusses | ℹ Chromadek ¦ Concrete Tiles ¦ Clay Tiles
💰 BUDGET PARAMETERS
Overall Budget (USD) | 45000 | ℹ Your total construction budget (excl. land)
Price Region | Harare (Base) | ℹ Harare (Base) ¦ Bulawayo (-10%) ¦ Secondary City (-15%)
Location Adjustment Factor | 100% | ℹ Auto-calculated from region
Contingency % | 12% | ℹ Recommended 10–15% for self-builders
🏢 CONTRACTOR DETAILS (fill if known)
Contractor / Vendor Name |  | ℹ Leave blank if not yet selected
NESTS Registration No. |  | ℹ e.g. NESTS-VND-00342
Contractor Grade | Grade A — Projects over $50,000
Proposed Workers on Site | 8
Warranty Period | 12 months defects liability
📊 YOUR PROJECT AT A GLANCE (auto-calculated)
Estimated $/m² (Budget ÷ Area) | $250
Budget excl. Contingency | 40178.5714
Contingency Amount | 4821.4286
NESTS Spot Checker Fee (7 stages) | 525
Est. Council Inspection Fees (ref) | 290
Total Project Cost Est. (incl. NESTS + Council) | 45815

## 🧱 Materials Estimator
🧱 MATERIALS COST ESTIMATOR — Zimbabwe 2026 Reference Prices
Blue cells = edit your quantities. Black cells = auto-calculated. Unit prices are 2026 Harare baselines — edit if you have actual quotes.
Location Factor (from Project Setup): |  |  | 100% | Applied to all unit prices automatically
Material / Item | Unit | Qty (You Edit) | Base Price (USD) 2026 | Adj. Price (× Location) | Total Cost (USD)
Phase A — Planning, Design & Council Approvals
Topographic Survey | survey | 1 | 350 | 350 | 350
Architectural Plan Drawing | set | 1 | 200 | 200 | 200
Structural Engineering Drawings | set | 1 | 200 | 200 | 200
Building Plan Submission Fee | lump | 1 | 300 | 300 | 300
Phase A — Planning, Design & Council Approvals — PHASE TOTAL |  |  |  |  | 1050
Phase B — Site Preparation
Site Clearing (labour + equipment) | lump | 1 | 800 | 800 | 800
Site Leveling & Grading | lump | 1 | 600 | 600 | 600
Setting Out / Pegging | lump | 1 | 150 | 150 | 150
Temporary Site Fencing | m run | 150 | 4.5 | 4.5 | 675
Phase B — Site Preparation — PHASE TOTAL |  |  |  |  | 2225
Phase C — Foundation Excavation & Construction
Soil Investigation / Bore Holes | test | 2 | 200 | 200 | 400
Foundation Trenching (excavation) | m³ | 30 | 22 | 22 | 660
Anti-Termite Treatment (Ant Proof) | m² | 180 | 3 | 3 | 540
Foundation Reinforcement Bar Y12 | tonne | 0.8 | 1350 | 1350 | 1080
Foundation Reinforcement Bar Y16 | tonne | 0.6 | 1350 | 1350 | 810
Binding Wire | roll | 3 | 12 | 12 | 36
Foundation Concrete (30MPa) | m³ | 18 | 155 | 155 | 2790
Damp Proof Course (DPC) Membrane | m run | 60 | 2.5 | 2.5 | 150
Blinding Concrete (lean mix) | m³ | 4 | 95 | 95 | 380
Phase C — Foundation Excavation & Construction — PHASE TOTAL |  |  |  |  | 6846
Phase D — Ground Floor Slab
Slab Reinforcement Bar Y10 | tonne | 0.9 | 1350 | 1350 | 1215
BRC Mesh (ref 193) | sheet | 12 | 45 | 45 | 540
Concrete Slab Pour (30MPa) | m³ | 22 | 155 | 155 | 3410
Slab Curing Compound | litre | 20 | 4.5 | 4.5 | 90
Formwork / Shuttering Timber | m² | 25 | 8 | 8 | 200
Phase D — Ground Floor Slab — PHASE TOTAL |  |  |  |  | 5455
Phase E — Walling
Common Bricks (per 1,000) | 1,000 | 28 | 72 | 72 | 2016
Face Bricks External (per 1,000) | 1,000 | 12 | 130 | 130 | 1560
Portland Cement (50kg bag) | bag | 280 | 12 | 12 | 3360
River Sand | m³ | 30 | 22 | 22 | 660
Pit Sand | m³ | 15 | 18 | 18 | 270
Building Lime (50kg bag) | bag | 25 | 6.5 | 6.5 | 162.5
Lintels (pre-cast concrete) | each | 18 | 28 | 28 | 504
Damp Proof Course (DPC) Strip | m run | 80 | 2.5 | 2.5 | 200
Wall Ties (galvanised) | bag | 5 | 12 | 12 | 60
Ring Beam Concrete (25MPa) | m³ | 4 | 145 | 145 | 580
Ring Beam Reinforcement Y10 | tonne | 0.3 | 1350 | 1350 | 405
Phase E — Walling — PHASE TOTAL |  |  |  |  | 9777.5
Phase G — Roof Structure & Covering
Timber Roof Trusses (pre-fab) | each | 14 | 120 | 120 | 1680
Wall-Plate Timber (50×76mm) | m run | 60 | 4.5 | 4.5 | 270
Chromadek IBR Roofing Sheets | sheet | 55 | 11 | 11 | 605
Roofing Nails & Screws | kg | 12 | 4 | 4 | 48
Ridge Capping | m run | 22 | 8 | 8 | 176
Fascia Board (152×19mm) | m run | 50 | 5 | 5 | 250
Gutters (PVC, 100mm) | m run | 40 | 6.5 | 6.5 | 260
Downpipes (PVC, 75mm) | m run | 20 | 5 | 5 | 100
Roof Underlay (sarking) | m² | 160 | 2.5 | 2.5 | 400
Phase G — Roof Structure & Covering — PHASE TOTAL |  |  |  |  | 3789
Phase I — Plumbing & Sanitation
HDPE Stormwater Pipe 110mm | m run | 50 | 6 | 6 | 300
HDPE Drain Pipe 160mm | m run | 30 | 9.5 | 9.5 | 285
First Fix Copper Pipe 15mm | m run | 80 | 8 | 8 | 640
First Fix Copper Pipe 22mm | m run | 40 | 12 | 12 | 480
Galv Steel Pipe (supply main) | m run | 15 | 14 | 14 | 210
WC Suite (close-coupled) | each | 3 | 180 | 180 | 540
Basin (vitreous china) | each | 3 | 85 | 85 | 255
Bath (acrylic 1500mm) | each | 1 | 220 | 220 | 220
Shower Tray & Fittings | each | 2 | 150 | 150 | 300
Kitchen Sink (double bowl SS) | each | 1 | 120 | 120 | 120
Geyser / Solar Hot Water | each | 1 | 450 | 450 | 450
Water Tank (5,000 litre) | each | 1 | 350 | 350 | 350
Inspection Chambers | each | 4 | 95 | 95 | 380
Phase I — Plumbing & Sanitation — PHASE TOTAL |  |  |  |  | 4530
Phase E2 — Internal Finishes
Internal Plaster (20mm) | m² | 550 | 4.5 | 4.5 | 2475
External Render | m² | 320 | 5.5 | 5.5 | 1760
Ceramic Floor Tiles (standard) | m² | 180 | 18 | 18 | 3240
Porcelain Floor Tiles (premium) | m² | 60 | 35 | 35 | 2100
Wall Tiles (bathrooms/kitchen) | m² | 80 | 22 | 22 | 1760
Tile Adhesive (25kg bag) | bag | 60 | 12 | 12 | 720
Tile Grout (5kg bag) | bag | 40 | 5.5 | 5.5 | 220
Screed (65mm) | m² | 180 | 8 | 8 | 1440
Ceiling Board (9.5mm gyproc) | m² | 200 | 12 | 12 | 2400
Ceiling Battens / Framing | m run | 350 | 3 | 3 | 1050
Coving / Cornices | m run | 120 | 4 | 4 | 480
Interior Paint (premium, 20L) | tin | 12 | 65 | 65 | 780
Exterior Paint / Plaster primer | tin | 8 | 70 | 70 | 560
PVA Sealer (20L) | tin | 6 | 35 | 35 | 210
Phase E2 — Internal Finishes — PHASE TOTAL |  |  |  |  | 19195
Phase E3 — Doors, Windows & Joinery
External Solid Timber Doors | each | 6 | 280 | 280 | 1680
Internal Hollow Core Doors | each | 10 | 90 | 90 | 900
Door Frames (timber) | each | 16 | 55 | 55 | 880
Door Hardware Sets (per door) | set | 16 | 35 | 35 | 560
Aluminium Windows (standard) | m² | 30 | 180 | 180 | 5400
Window Burglar Bars (steel) | m² | 30 | 45 | 45 | 1350
Kitchen Cupboards (base) | m run | 4 | 280 | 280 | 1120
Kitchen Cupboards (wall) | m run | 4 | 220 | 220 | 880
Wardrobes / Built-in Cupboards | m run | 8 | 200 | 200 | 1600
Phase E3 — Doors, Windows & Joinery — PHASE TOTAL |  |  |  |  | 14370
Phase J — Electrical Installation
Electrical Cable (2.5mm TPS) | m run | 250 | 2.5 | 2.5 | 625
Electrical Cable (1.5mm TPS) | m run | 120 | 1.8 | 1.8 | 216
DB Box (18 way) | each | 2 | 95 | 95 | 190
Power Points (double) | each | 25 | 18 | 18 | 450
Light Points | each | 22 | 12 | 12 | 264
MCB / Circuit Breakers | each | 20 | 12 | 12 | 240
Earth Leakage Unit | each | 2 | 65 | 65 | 130
Light Fittings (standard) | each | 20 | 25 | 25 | 500
Conduit PVC (25mm) | m run | 150 | 2 | 2 | 300
ZESA Connection / Service | lump | 1 | 800 | 800 | 800
Phase J — Electrical Installation — PHASE TOTAL |  |  |  |  | 3715
Phase K — External Works
Paving Bricks / Driveway | m² | 80 | 22 | 22 | 1760
Palisade Fencing (steel 1.8m) | m run | 60 | 55 | 55 | 3300
Boundary Wall (face brick 1.8m) | m run | 40 | 85 | 85 | 3400
Gate (electric steel double) | each | 1 | 1200 | 1200 | 1200
Borehole Drilling & Casing | lump | 1 | 2500 | 2500 | 2500
Borehole Pump & Plumbing | lump | 1 | 950 | 950 | 950
Septic Tank (3,000L) | each | 1 | 650 | 650 | 650
Landscaping / Topsoil | m² | 200 | 5 | 5 | 1000
Soakaway / Soak-pit | each | 1 | 350 | 350 | 350
Phase K — External Works — PHASE TOTAL |  |  |  |  | 15110
Solar & Energy Resilience
Solar Panels (400W each) | each | 8 | 220 | 220 | 1760
Solar Inverter (5kVA Hybrid) | each | 1 | 1200 | 1200 | 1200
Battery Bank (200Ah lithium) | each | 2 | 950 | 950 | 1900
Solar Cabling & Mounting | lump | 1 | 400 | 400 | 400
Generator (6kVA backup) | each | 1 | 850 | 850 | 850
Solar & Energy Resilience — PHASE TOTAL |  |  |  |  | 6110
🏗️ GRAND TOTAL — ALL MATERIALS (excl. Labour) |  |  |  |  | 92172.5

## 👷 Labour Rates
👷 LABOUR RATES — Zimbabwe 2026 ¦ NEC Construction Industry Rates + Market Estimates
Source: NEC-CI Circular 02/2024 (effective 1 April 2024) · Statutory Instrument 45/2013 · RemotePeople · Playroll · WorldSalaries.com
📋 NEC CONSTRUCTION INDUSTRY MINIMUM WAGE RATES (effective 1 April 2024)
Grade / Trade | Hourly Rate (USD) | Weekly Rate (USD) | Standard Hrs/Week | Source
General Labourer (Grade 1 — Exempt Worker) | 1.57 | 69.24 | 44 | NEC-CI Circ. 02/2024
General Labourer (Grade 1B — Floorlayer) | 1.65 | 72.63 | 44 | NEC-CI Circ. 02/2024
Skilled Worker — Grade 2 | 2.15 | 94.42 | 44 | NEC-CI Circ. 02/2024
Skilled Worker — Grade 3 | 2.34 | 103.13 | 44 | NEC-CI Circ. 02/2024
Skilled Worker — Grade 4 (Trade Worker) | 2.72 | 119.59 | 44 | NEC-CI Circ. 02/2024
Skilled Worker — Grade 4B (BEIWM) | 2.51 | 110.39 | 44 | NEC-CI Circ. 02/2024
💼 MARKET RATE ESTIMATES (indicative — above NEC minimum)
Role / Trade | Est. Daily Rate (USD) | Est. Monthly (USD) | Notes | Basis
General Labourer (informal / self-build) | 5–15 | 110–330 | Negotiated daily rate, cash | Market
Bricklayer (skilled) | 15–30 | 330–660 | Per day including tools | Market
Plasterer (skilled) | 15–35 | 330–770 | Per day or per m² | Market
Plumber (qualified) | 20–50 | 440–1,100 | Per day or per point | Market
Electrician (qualified) | 20–50 | 440–1,100 | Per day or per point | Market
Foreman / Site Supervisor | 35–80 | 770–1,760 | Experience-dependent | Market
Civil / Structural Engineer | — | 800–1,500 | Monthly salary / consultant | Market
Architect / Quantity Surveyor | — | 700–1,200 | Monthly salary / consultant | Market
National Average (all sectors, Q1 2026) | — | 190–210 | USD equiv. from ZWG salary | Playroll 2026
Statutory Minimum Wage (all sectors) | — | 150 | USD/month government minimum | RemotePeople 2026
🧮 LABOUR BUDGET ESTIMATOR — Estimate days per phase, tool auto-totals
Phase / Trade Category | Team Size (people) | Est. Duration (days) | Avg Day Rate (USD/person) | Total Labour Cost (USD)
Planning & Survey | 1 | 5 | 35 | 175
Site Preparation | 4 | 10 | 12 | 480
Foundation Excavation | 6 | 12 | 12 | 864
Foundation & Slab Concrete | 5 | 8 | 15 | 600
Walling (bricklayers + labourers) | 8 | 30 | 15 | 3600
Roof Structure Erection | 5 | 10 | 20 | 1000
Roof Covering (Chromadek) | 4 | 5 | 18 | 360
Plumbing — First Fix | 2 | 10 | 35 | 700
Plumbing — Second Fix | 2 | 8 | 35 | 560
Electrical — First Fix | 2 | 12 | 35 | 840
Electrical — Second Fix | 2 | 8 | 35 | 560
Internal Plastering | 4 | 20 | 18 | 1440
Tiling & Screeding | 3 | 15 | 20 | 900
Painting | 3 | 12 | 18 | 648
Joinery & Fitting | 2 | 8 | 25 | 400
External Works | 4 | 15 | 15 | 900
Supervision (Foreman) | 1 | 180 | 50 | 9000
👷 TOTAL ESTIMATED LABOUR COST |  |  |  | 23027

## 🔍 Spot Checker
🔍 NESTS SPOT CHECKER — Independent Inspection Gate System
NESTS independently verifies construction quality at 7 key stages. Payment to the vendor is LOCKED until each stage is approved. These fees are SEPARATE from your build budget.
HOW IT WORKS — WHAT THE CLIENT SEES ON THE NESTS PLATFORM
1. When you post a project on NESTS, the 7 Spot Checker gates are automatically built into your milestone plan.
2. Each Spot Checker stage is triggered when the vendor reports that phase is complete.
3. A NESTS-registered independent inspector visits the site within 48 hours and verifies compliance with Zimbabwe Building Standards.
4. If the stage PASSES: the next milestone payment is UNLOCKED and the vendor can proceed.
5. If the stage FAILS: the vendor must rectify defects before re-inspection. No payment is released.
6. The Spot Checker fee ($75 per stage × 7 stages = $525 total) is paid by the client to NESTS — separate from the vendor contract.
7. Council inspection fees (approx. $290 for Stages 1–6, variable for Stage 7) are paid directly to Harare City Council.
THE 7 SPOT CHECKER STAGES — AS SHOWN ON THE NESTS VENDOR BID SCREEN
Stage | Stage Name | What Is Inspected | NESTS Fee (USD) | Council Fee (Est. USD)
Stage 1 | Stage 1 — Siting | Foundation Trenching — depth, width, soil bearing verified | 75 | 35
Stage 2 | Stage 2 — Compaction | Concrete Footing & Backfill — compaction test, mix verified | 75 | 45
Stage 3 | Stage 3 — Lintel Level | Door-Height & Ring Beam — reinforcement placement verified | 75 | 50
Stage 4 | Stage 4 — Wall-Plate | Gable Construction — wall-plate fixing, tie-down verified | 75 | 50
Stage 5 | Stage 5 — Roofing | Truss Structural Integrity — span, pitch, bracing verified | 75 | 55
Stage 6 | Stage 6 — Plumbing | Drainage & Internal Systems — pressure test, gradient verified | 75 | 55
Stage 7 | Stage 7 — Final | Certificate of Occupation — full compliance survey | 75 | Variable
TOTAL SPOT CHECKER FEES |  |  | 525 | ~$290 (est. Stages 1–6)

## 📊 Bid Summary
📊 NESTS PLATFORM — PROJECT BID SUMMARY
This sheet mirrors the downloadable bid document generated by NESTS after a vendor submits their quote. Use it as a reference to understand what vendors will see and submit.
PROJECT DETAILS
Project Name | Harare Residential Build — 4-Bedroom
Client | Sarah M.
Location | Borrowdale, Harare
House Type | 4-Bedroom Executive
Floor Area (m²) | 180
Start Date | 20 Jun 2026
Target Completion | 31 Dec 2026
Contractor | 0
NESTS Reg No. | 0
Export Date | 2026-04-29
COST BREAKDOWN BY PHASE (Materials — from 🧱 Materials Estimator)
Phase / Category | Est. Materials Cost (USD) | % of Materials Budget
Phase A — Planning, Design & Council Approvals | 1050 | 1.139%
Phase B — Site Preparation | 0 | 0%
Phase C — Foundation Excavation & Construction | 0 | 0%
Phase D — Ground Floor Slab | 2016 | 2.187%
Phase E — Walling | 270 | 0.2929%
Phase G — Roof Structure & Covering | 640 | 0.6944%
Phase I — Plumbing & Sanitation | 2100 | 2.278%
Phase E2 — Internal Finishes | 5400 | 5.859%
Phase E3 — Doors, Windows & Joinery | 240 | 0.2604%
Phase J — Electrical Installation | 650 | 0.7052%
Phase K — External Works | 92172.5 | 100%
Solar & Energy Resilience | 0 | 0%
TOTAL MATERIALS | '🧱 Materials Estimator'!G145 | 100.0%
GRAND TOTAL COST SUMMARY
Total Materials Cost | '🧱 Materials Estimator'!G145
Total Labour Cost (estimated) | '👷 Labour Rates'!F47
Sub-Total (Materials + Labour) | 115199.5
Contingency (from Project Setup) | 13823.94
NESTS Spot Checker Fee (7×$75) | 525
Council Inspection Fees (est.) | 290
TOTAL PROJECT COST (ALL-IN EST.) | 129838.44
Your Overall Budget | 45000
Variance (Budget vs Estimate) | -84838.44
ℹ Positive variance = you are within budget. Negative variance = your estimate exceeds budget — review quantities or adjust your overall budget.
MILESTONE PAYMENT SCHEDULE (matches NESTS Vendor Bid format)
Milestone ID | Description | Payment % | Target Date
A1 | Topographic Survey | 3% | 20 Jun 2026
A2 | Architectural Plan Drawing | 4% | 30 Jun 2026
A3 | Structural Engineering Drawings | 3% | 10 Jul 2026
A4 | Building Plan Submission | 2% | 20 Jul 2026
B1 | Site Clearing | 3% | 01 Aug 2026
B3 | Site Leveling & Grading | 3% | 10 Aug 2026
B4 | Setting Out / Pegging | 2% | 14 Aug 2026
C1 | Soil Investigation | 2% | 15 Aug 2026
C2 | Foundation Trenching | 5% | 22 Aug 2026
C3 | Anti-Termite Treatment | 2% | 24 Aug 2026
C5 | Foundation Reinforcement | 4% | 28 Aug 2026
⛔ | SPOT CHECKER STAGE 1 — Siting | — | Auto
C7 | Foundation Concrete Pour | 6% | 15 Sep 2026
C8 | Damp Proof Course (DPC) | 2% | 18 Sep 2026
D4 | Slab Reinforcement | 4% | 22 Sep 2026
⛔ | SPOT CHECKER STAGE 2 — Compaction | — | Auto
D6 | Concrete Slab Pour | 6% | 05 Oct 2026
D7 | Slab Curing | 2% | 12 Oct 2026
E1 | Plinth Course Brickwork | 3% | 15 Oct 2026
E2 | External Walling | 8% | 01 Nov 2026
E3 | Internal Partition Walls | 4% | 10 Nov 2026
⛔ | SPOT CHECKER STAGE 3 — Lintel | — | Auto
⛔ | SPOT CHECKER STAGE 4 — Wall-Plate | — | Auto
G3 | Roof Truss Erection | 5% | 20 Nov 2026
⛔ | SPOT CHECKER STAGE 5 — Roofing | — | Auto
G6B | Chromadek Roof Sheets | 5% | 10 Dec 2026
G7 | Gutters & Downpipes | 2% | 15 Dec 2026
I1 | Stormwater Drainage | 3% | 10 Dec 2026
I3 | First Fix Plumbing | 3% | 20 Dec 2026
⛔ | SPOT CHECKER STAGE 6 — Plumbing | — | Auto
O1 | Snagging List Completion | 4% | 28 Dec 2026
⛔ | SPOT CHECKER STAGE 7 — Final | — | Auto
O3 | Certificate of Occupation | 5% | 31 Dec 2026

## 📚 References
📚 DATA SOURCES & REFERENCES
All prices and indices used in this tool are sourced from the following publicly available and reputable sources. Accessed April 2026.
# | Source | What It Covers / URL
1 | ZimStat — Zimbabwe National Statistics Agency | BMPI & CEMPI Q1 2026 data. Building Materials Price Index (quarterly). Civil Engineering Materials Price Index (monthly). zimstat.co.zw/building-material-price-index
2 | Bulawayo24 News — April 28 2026 | Construction Costs Rise in Zimbabwe as Material Prices Climb. Civil materials USD +6.7% Mar 2026; BMPI ZWG +4.1% Q1 2026. bulawayo24.com
3 | ZimEye — April 28 2026 | Zimbabwe's Inflation Rises — CEMPI jumped to 209.88 in March from 195.92 in February (+7.1% MoM). zimeye.net
4 | CAHF — Africa Housing Finance Yearbook 2024 | Zimbabwe housing deficit, cement prices (US$10/50kg bag), construction cost range (US$250–500/m²), mortgage penetration (0.4% GDP). housingfinanceafrica.org
5 | AECOM — Africa Property & Construction Cost Guide 2024/25 | Regional construction benchmarks across Sub-Saharan Africa. aecom.com
6 | NEC-CI — National Employment Council for the Construction Industry | Circular 02/2024: Minimum Wage Rates for Construction Workers, effective 1 April 2024. Statutory Instrument 45/2013. NEC hourly/weekly rates by grade.
7 | RemotePeople — Minimum Wage in Zimbabwe 2026 | Statutory minimum wage US$150/month; NEC sector benchmarks; market rate context. remotepeople.com
8 | Playroll — Zimbabwe EOR Guide (February 2026) | Average gross monthly salary ZWL 1.9–2.1M (~US$190–210); annual inflation ~20–30% late 2025/early 2026. playroll.com
9 | WorldSalaries.com — Construction Worker Salary Zimbabwe 2025 | Average annual construction worker salary data by experience grade. worldsalaries.com
10 | EstimationQS.com — Building Costs Per Square Metre in Zimbabwe (2025) | Construction sector GDP contribution US$1.1B Q1 2025; steel US$1,200–1,500/t; cement US$10–15/bag; labour 25–30% of budgets. estimationqs.com
11 | Property.co.zw — Buy or Build in Zimbabwe 2025 | 3-bed Harare avg US$180,000; Bulawayo US$125,000; build cost US$80–300/m². property.co.zw
12 | Palmer Construction Zimbabwe — Cost Estimations | Standard house US$80–120/m²; 3-bed approx. US$12,800; 4-bed approx. US$14,400. palmer.co.zw
13 | Mukamba Real Estate — Zimbabwe Property Market 2025 | Housing backlog ~1.5M units; population projection 21.2M by 2042. mukamba.co.zw
14 | Equity Axis — ZimProp Expo 2025 | Harare average US$240,000; US$421/m²; diaspora remittances US$1.8B 2024; digital search 92%. equityaxis.net
15 | NewsDay / Zimbabwe Independent — July 2025 | Mortgage rates 20–25% p.a.; mortgage penetration 0.4% of GDP; 16,500 Epworth demolitions. newsday.co.zw
16 | ZBMS — Zimbabwe Building Materials Suppliers | Live product price listings for Harare market. zbms.co.zw
17 | Builders Express Zimbabwe — Roofing Prices 2024 | Chromadek IBR roofing sheets, Qtile and concrete tile price data. builders.co.zw
18 | ZimCompass / Classifieds.co.zw | Brick and aggregate market classified listings — semi-common bricks US$55/1,000. zimcompass.com
19 | Reall.net — Zimbabwe Country Dashboard | Housing deficit 1.5M units; 72% below poverty line; ShelterSol affordable housing. reall.net
20 | Accio.com — Roofing Tiles Prices Zimbabwe 2025 | Market size US$12M; CAGR 4–6%; supplier price ranges US$1.10–4.50/piece. accio.com
⚠ DISCLAIMER: All prices are indicative estimates for budgeting guidance only. NESTS accepts no liability for decisions made on the basis of this tool. Always consult a qualified quantity surveyor for formal estimates. Prices vary by location, supplier, and project scale. © 2026 NESTS. All rights reserved.